## Definitions
Definition - A Risk is not an Issue
A project risk is defined as an uncertain event or condition that, if it occurs, has a positive or a negative effect on a project objective.
While the process for managing risks that have positive or negative effects are the same, most activities associated with “traditional” project risk management have focused on mitigating the negative threats to a project’s success.
An issue is defined as any functional, technical or business-related event that arises during the course of a project that requires a satisfactory resolution for the project to proceed as planned and are outside the ability or scope of the project team to resolve.
An issue is known to have already occurred and needs an immediate resolution whereas a risk has a potential of occurrence. A risk if not mitigated could evolve into an issue.
Describing a Risk
The following structure should be used: There is a risk that {the new risk} because {the causes of the risk} therefore {the impacts of the risk} may happen or If {the new risk} because {the causes of the risk} then {the impacts of the risk} may happen
Example: A project has the objective of completing the acceptance of a software module by date x within a budget of y with resources z.
There is a risk that: Acceptance is not achieved by date x
Because: The complexity of the requirement was misunderstood The development language is unfamiliar to resources z The acceptance criteria are ambiguous
Therefore: Additional development time will be required, exceeding Budget Unplanned resources will have to be recruited The Project Team will be subject

## Matrix
Risks and Issues Rating Matrix
Risk Ratings
Impact
[5 empty] | Catastrophic Likely catastrophic events resulting in project failure and benefits not being realised | Major Likely to cause significant disruption to the project, resulting in the need to conduct re-planning and re-estimating. In the extreme, it may result in failure of the project | Moderate Likely to cause delays or additional work that would exceed existing contingencies, resulting in exceeded time scales, additional resource and/or additional budget requirements | Minor Likely to cause delays or additional work that could be contained within existing contingencies | Minimal Likely to cause negligible delays
Likelihood
Probability | Frequency
96% - 100% | Is expected to occur in most circumstances | Likelihood | 5 | Almost Certain | Extreme | Extreme | High | Medium | Medium
71% - 95% | Will probably occur in most circumstances |  | 4 | Likely | Extreme | Extreme | High | Medium | Medium
31% - 70% | Might occur at some time |  | 3 | Possible | Extreme | High | Medium | Medium | Low
5% - 30% | Could occur at some time |  | 2 | Unlikely | High | High | Medium | Low | Low
< 5% | May only occur in exceptional circumstances |  | 1 | Rare | High | Medium | Medium | Low | Low
[5 empty] | Catastrophic | Major | Moderate | Minor | Minimal
[5 empty] | 1 | 2 | 3 | 4 | 5
Issues Ratings
Impact
[5 empty] | 1 | 2 | 3 | 4 | 5
[5 empty] | Catastrophic | Major | Moderate | Minor | Minimal
[5 empty] | Extreme | Extreme | High | Medium | Medium

## Risks and Issues Register
|  | Category |  |  |  | Likelihood | Impact |  |  | Overall assessment: |  | Rating | Status
|  | People |  |  |  | Almost Certain | Minimal |  |  | RED Significant project risks exist which will impact overall project success if not addressed immediately |  | Low | Open
|  | Time |  |  |  | Likely | Minor |  |  | AMBER Project risks exist which may have an adverse impact on project success if not addressed within a reasonable timeframe |  | Medium | In Analysis
|  | Quality |  |  |  | Possible | Moderate |  |  | GREEN Processes are in place to effectively manage project risks |  | High | PM Review
|  | Budget and costs |  |  |  | Unlikely | Major |  |  |  |  | Extreme | SC Review
[6 empty] | Rare | Catastrophic | [5 empty] | Cancelled
Convert to Issue
In Mitigation
Closed
Project Name | [5 empty] | Overall assessment:
[6 empty] | Date: | 2014-12-15
PROJECT RISK REGISTER
Risk No | Date Raised | Risk Category | Risk Title / Description There is a risk that... (new risk) | Potential Causes because... (the cause of the risk) | Potential Impact on Plan therefore… (the impact of the risk) | Likelihood | Impact | Risk Rating | Current/Proposed Mitigation Strategy | By When | Responsible | Rating post mitigation strategy | Status | Progress / Comment
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
|  |  | <<< Leave this row blank. To add a new row insert a line before this >>> |  |  |  |  | #N/A
PROJECT ISSUE REGISTER
Issue No | Date Raised | Issue Category | Risk Title / Description There is an issue that… (new issue) | Potential Causes because… (the cause of the issue) | Potential Impact on Plan therefore... (the impact of the issue) |  | Impact | Risk Rating | Current/Proposed Mitigation Strategy | By When | Responsible | Rating post mitigation strategy | Status | Progress / Comment
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
|  |  | <<< Leave this row blank. To add a new row insert a line before this >>> |  |  |  |  | #N/A
Note on O6: EDS Australia: The formula in column M, to calculate the Likelihood_Impact, makes reference to this cell - to exclude the risk from the open risks count.
Note on O7: EDS Australia: The formula in column M, to calculate the Likelihood_Impact, makes reference to this cell - to exclude the risk from the open risks count.
Note on O9: EDS Australia: The formula in column M, to calculate the Likelihood_Impact, makes reference to this cell - to exclude the risk from the open risks count.
Note on J11: Complete this section once all risks and issues are assessed

## Action Map
Action Required
The Project Lead is responsible for following up the status of risks and issues on (I) the due date of the action, and (ii) for each Project meeting update.
Risk / Issue Rating | Urgency of Action | Level of Management for Action | Reporting | Potential Project Outcomes | Mitigation Actions
Extreme | Immediate action | Steering Committee | Program Director / CE | This could result in the failure of the project | * Requires essential allocation of resources within the project to mitigate the risk. * Establish plans and countermeasures. * Assign a person to constantly monitor the risk.
High | Action as soon as practicable | Project Sponsor | Steering Committee | This will impact the project by delaying completion or requiring investment of additional resources with a consequential increase in costs or the need to re-plan the work. | * Require priority allocation of resources within the project to mitigate the risk. * Establish plans and countermeasures. * Assigned person monitors the risk at intervals.
Medium | Action timetable must be specified | Project Manager | Program Manager | It may be that the disruption cannot be contained within existing time or budget contingency. May need to accept and bear the consequences. | * Allocation of resources for study of the risk is desirable. * Nominated person monitors the risk periodically.
Low | Normal | As appropriate | As appropriate | There is sufficient contingency built into the project to contain the risk. | * Risk identified and included in risk report. * Risk reviewed periodically.